## WLM Req
Requirements | Description | Phase 1(Oct-Dec) | Phase 2 | Future Roadmap | Dependency
Capability should be able to integrate with multiple APM platforms for automated retreival of source data, with filetring on multiple selection criteria | Should be able support integration through APIs with datadog and App insights |  | I
Capability should be having an user interface to consume source data through CSV format (if format can be customized?) | The CSV file format should be provided, and the user interface should be able to read the file and generate the report accordingly. | I
Capability should provide an option to customize the final prompt for any modifications based on application needs(Access based edit) | The default prompt should be customizable based on application needs | I
Capability should provide an option for RAG implementation with periodic updates for the same model(Access based edit) | Option to provide more context through periodic updates for RAG definition | I(Team to get back )
Capability should provide all possible types of test recommendations along with justification | Types of performance tests required to be recommended - like stress,spike,load tests along with prodution snapshots providing details the time stamp | I
Capability should provide WLM recommendation for enviorment sizing similar to production or at reduced capacity also | WLM recommndation to be modified with statistical exploration based on scaled comparison of test and prod environments | I(Preliminary)
Capability should be able to add recommendation and justify the need of performance testing | Some applications may not have consistent performance testing but can still experience slowness in production due to multiple factors. In such cases, the capability should be able to analyze production metrics and recommend whether performance testing is necessary suitable towards stakeholders | I
Mapping between number of users and TPH should be reflecting production behavior in recommendation section | Recommendations should closely reflect production peaks in terms of Users, hits, transactions etc | I
Capability should be built as an agent for future consumption across different platforms | Future PWC AI hub architecture could use this agent with MCP protocol to achieve a common end to end goal | I
Capability should be able to provide recommendations on test users required to execute performance tests. | Based on source metrics and lower environment sizing, the count of test data required to execute performance tests should be determined. Certain applications may need only unique users for testing. WLM should be able to provide recommendations on usage of appropriate test users. | I(Preliminary)
Capability should be able to analyze source response times and provide recommendations on SLAs. | Some applications are exposed to consistent changes in load patterns with ever growing needs and enhancements. In this way the model should analyze trend of response times to suggest any possible revisions on response SLAs | I(Preliminary)
Capability should refine WLM model by specifying distribution of load based on geographical sources | App insights should be able to volumetric for geographic.Based on production geographic volume,we can setup load test agents and can execute performance tests according to production usage based on location patterns | I
Capability should be able to provide pacing and think time required for performance tests | Based on user volume and concurrency,WLM should be able to define pacing,think time and concurrent users required to achieve the expected Volume/TPS. | I
WLM for GreenField applications | Capability should be able to recommend workload model on GreenField applications if the usage is similar to the existing application with requirerements provided from new application |  |  | I

## Option 1 (Existing RAG)
Requirements | Description | Phase 1(Oct-Dec) | Phase 2 | Future State | Comments from QZ | Dependences
Capability should be able to integrate with multiple APM platforms for automated retreival of source data, with filetring on multiple selection criteria | Should be able support integration through APIs with datadog and App insights | I |  |  | We will begin with two APM tools: Datadog and App Insights | Multiple APM tools should be integrated with our application, and RUM data should be available.
Capability should be having an user interface to consume source data through CSV format (if format can be customized?) | The CSV file format should be provided, and the user interface should be able to read the file and generate the report accordingly. | I |  |  | UI is minimal , so moved to Future state,. However the solution will provide minimal UI to work as expected | The CSV should be structured according to our format. The source file must include the following fields on an hourly basis: page path, timestamp, views/TPS, and active users.
Capability should provide an option to customize the final prompt for any modifications based on application needs(Access based edit) | The default prompt should be customizable based on application needs | I
Capability should provide an option for RAG implementation with periodic updates for the same model(Access based edit) | Option to provide more context through periodic updates for RAG definition | I |  |  | Resue the existing RAG built for Code Context AI Hub with separate data collector - Should able to accomdate in same timeline but will add additonal AI Developer | The existing RAG code context model is not useful for our workload model prototype, but we can leverage the existing RAG infrastructure for the ingestion context required for this solution, or else we can build a separate standalone RAG ingestion solution.
Capability should provide all possible types of test recommendations along with justification | Types of performance tests required to be recommended - like stress,spike,load tests along with prodution snapshots providing details the time stamp | I |  |  | Scalability and volume tests will require additional information; we will structure it and come up with the approach
Capability should provide WLM recommendation for enviorment sizing similar to production or at reduced capacity also | WLM recommndation to be modified with statistical exploration based on scaled comparison of test and prod environments | I |  |  | Sizing Needs based on prompt context provided for each AUT. Yes, can be added based on Production logsand sizing inputs | Prodution vs target Environment Configuration should be provided.
Capability should be able to add recommendation and justify the need of performance testing | Some applications may not have consistent performance testing but can still experience slowness in production due to multiple factors. In such cases, the capability should be able to analyze production metrics and recommend whether performance testing is necessary suitable towards stakeholders | I
Mapping between number of users and TPH should be reflecting production behavior in recommendation section | Recommendations should closely reflect production peaks in terms of Users, hits, transactions etc | I
Capability should be built as an agent for future consumption across different platforms | Future PWC AI hub architecture could use this agent with MCP protocol to achieve a common end to end goal |  |  | I | Option 2 : In this Option moving to Future state but in Option 2 we have outlined the same
Capability should be able to provide recommendations on test users required to execute performance tests. | Based on source metrics and lower environment sizing, the count of test data required to execute performance tests should be determined. Certain applications may need only unique users for testing. WLM should be able to provide recommendations on usage of appropriate test users. | I
Capability should be able to analyze source response times and provide recommendations on SLAs. | Some applications are exposed to consistent changes in load patterns with ever growing needs and enhancements. In this way the model should analyze trend of response times to suggest any possible revisions on response SLAs |  | I |  | A new set of prompts and context must be developed to generate response-time–based SLA recommendations.
Capability should refine WLM model by specifying distribution of load based on geographical sources | App insights should be able to volumetric for geographic.Based on production geographic volume,we can setup load test agents and can execute performance tests according to production usage based on location patterns |  | I |  | New context shall be provided, and upon successful model functional, this will be implemented in Phase 2
Capability should be able to provide pacing and think time required for performance tests | Based on user volume and concurrency,WLM should be able to define pacing,think time and concurrent users required to achieve the expected Volume/TPS. | I | I |  | We will attempt to implement this in Phase 1 if time permits; otherwise, it will be deferred to Phase 2
WLM for GreenField applications | Capability should be able to recommend workload model on GreenField applications if the usage is similar to the existing application with requirerements provided from new application |  |  | I | New Applications predicatability only

## Option 2 (AgenticAI)
Requirements | Description | Phase 1(Oct-Dec) | Phase 2 | Future State | Comments from QZ | Dependences
Capability should be able to integrate with multiple APM platforms for automated retreival of source data, with filetring on multiple selection criteria | Should be able support integration through APIs with datadog and App insights | I |  |  | We will begin with two APM tools: Datadog and App Insights | Multiple APM tools should be integrated with our application, and RUM data should be available.
Capability should be having an user interface to consume source data through CSV format (if format can be customized?) | The CSV file format should be provided, and the user interface should be able to read the file and generate the report accordingly. | I |  |  | UI is minimal , so moved to Future state,. However the solution will provide minimal UI to work as expected | The CSV should be structured according to our format. The source file must include the following fields on an hourly basis: page path, timestamp, views/TPS, and active users.
Capability should provide an option to customize the final prompt for any modifications based on application needs(Access based edit) | The default prompt should be customizable based on application needs | I
Capability should provide an option for RAG implementation with periodic updates for the same model(Access based edit) | Option to provide more context through periodic updates for RAG definition | I | I |  | we need to build standalone Agentic RAG that can be self-managed by agents and goes in two phases
Capability should provide all possible types of test recommendations along with justification | Types of performance tests required to be recommended - like stress,spike,load tests along with prodution snapshots providing details the time stamp | I |  |  | Scalability and volume tests will require additional information; we will structure it and come up with the approach
Capability should provide WLM recommendation for enviorment sizing similar to production or at reduced capacity also | WLM recommndation to be modified with statistical exploration based on scaled comparison of test and prod environments | I |  |  | Sizing Needs based on prompt context provided for each AUT. Yes, can be added based on Production logsand sizing inputs | Prodution vs target Environment Configuration should be provided.
Capability should be able to add recommendation and justify the need of performance testing | Some applications may not have consistent performance testing but can still experience slowness in production due to multiple factors. In such cases, the capability should be able to analyze production metrics and recommend whether performance testing is necessary suitable towards stakeholders | I
Mapping between number of users and TPH should be reflecting production behavior in recommendation section | Recommendations should closely reflect production peaks in terms of Users, hits, transactions etc | I
Capability should be built as an agent for future consumption across different platforms | Future PWC AI hub architecture could use this agent with MCP protocol to achieve a common end to end goal | I | I |  | Added additonal AI Developer to build the same in Ph1 and 2 (More realistic Logic , reasoning and Planning and decision making based on goal)
Capability should be able to provide recommendations on test users required to execute performance tests. | Based on source metrics and lower environment sizing, the count of test data required to execute performance tests should be determined. Certain applications may need only unique users for testing. WLM should be able to provide recommendations on usage of appropriate test users. | I
Capability should be able to analyze source response times and provide recommendations on SLAs. | Some applications are exposed to consistent changes in load patterns with ever growing needs and enhancements. In this way the model should analyze trend of response times to suggest any possible revisions on response SLAs |  | I |  | A new set of prompts and context must be developed to generate response-time–based SLA recommendations.
Capability should refine WLM model by specifying distribution of load based on geographical sources | App insights should be able to volumetric for geographic.Based on production geographic volume,we can setup load test agents and can execute performance tests according to production usage based on location patterns |  | I |  | New context shall be provided, and upon successful model functional, this will be implemented in Phase 2
Capability should be able to provide pacing and think time required for performance tests | Based on user volume and concurrency,WLM should be able to define pacing,think time and concurrent users required to achieve the expected Volume/TPS. | I | I |  | We will attempt to implement this in Phase 1 if time permits; otherwise, it will be deferred to Phase 2
WLM for GreenField applications | Capability should be able to recommend workload model on GreenField applications if the usage is similar to the existing application with requirerements provided from new application |  |  | I | New Applications predicatability only